## Reports
Report ID | Technician ID | Technician | Project | Location | Date Begin | Time Begin | Date End | Time End | Hours | Comments | Created At | Updated At
24 | 5 | Ricardo Morales | tycos3120 | 23 tycos | 2025-11-17 | 08:00 | 2025-11-17 | 19:00 | 11 | install 30 lights, removed cabinets, install new door | 2025-11-18T00:05:42 | 2025-11-18T00:07:12
28 | 4 | Vincent Vincent | tycos3120 | 23 tycos | 2025-11-14 | 08:00 | 2025-11-14 | 20:00 | 12 | install 30 lights, removed cabinets, install new door | 2025-11-18T00:15:10 | 2025-11-18T00:15:10
23 | 5 | Ricardo Morales | Tycos3120 | Tycos st | 2025-11-13 | 08:00 | 2025-11-13 | 21:00 | 13 | repair, painting, install etc | 2025-11-17T00:04:08 | 2025-11-17T00:04:08
27 | 4 | Vincent Vincent | tycos3120 | 23 tycos | 2025-11-13 | 08:00 | 2025-11-13 | 18:00 | 10 | install 30 lights, removed cabinets, install new door | 2025-11-18T00:14:56 | 2025-11-18T00:14:56
22 | 5 | Ricardo Morales | Tycos3120 | Tycos st | 2025-11-12 | 08:00 | 2025-11-12 | 20:00 | 12 | repair, painting, install etc | 2025-11-17T00:03:50 | 2025-11-17T00:03:50
26 | 4 | Vincent Vincent | tycos3120 | 23 tycos | 2025-11-12 | 11:00 | 2025-11-12 | 18:00 | 7 | install 30 lights, removed cabinets, install new door | 2025-11-18T00:14:38 | 2025-11-18T00:14:38
25 | 4 | Vincent Vincent | tycos3120 | 23 tycos | 2025-11-11 | 18:00 | 2025-11-12 | 07:00 | 13 | install 30 lights, removed cabinets, install new door | 2025-11-18T00:14:01 | 2025-11-18T00:14:01
21 | 5 | Ricardo Morales | Tycos3120 | Tycos st | 2025-11-11 | 08:00 | 2025-11-11 | 20:00 | 12 | repair, painting, install etc | 2025-11-17T00:03:39 | 2025-11-17T00:03:39
20 | 5 | Ricardo Morales | Tycos3120 | Tycos st | 2025-11-10 | 08:00 | 2025-11-10 | 20:00 | 12 | repair, painting, install etc | 2025-11-17T00:03:25 | 2025-11-17T00:03:25
14 | 4 | Vincent Vincent | Tycos | 17 Tycos S. | 2025-10-31 | 08:00 | 2025-10-31 | 21:00 | 13 | pending some panels and lights | 2025-11-02T20:03:44 | 2025-11-02T20:03:44
19 | 5 | Ricardo Morales | CityHall | 17 King St. | 2025-10-31 | 08:00 | 2025-10-31 | 20:00 | 12 | pending some panels and lights | 2025-11-02T20:07:29 | 2025-11-02T20:07:29
9 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-31 | 08:00 | 2025-10-31 | 20:00 | 12 | pending some painting | 2025-11-02T17:41:14 | 2025-11-02T17:41:14
13 | 4 | Vincent Vincent | Tycos | 17 Tycos S. | 2025-10-30 | 08:00 | 2025-10-30 | 21:00 | 13 | pending some panels and lights | 2025-11-02T20:03:23 | 2025-11-02T20:03:23
18 | 5 | Ricardo Morales | CityHall | 17 King St. | 2025-10-30 | 08:00 | 2025-10-30 | 20:00 | 12 | pending some panels and lights | 2025-11-02T20:07:16 | 2025-11-02T20:07:16
8 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-30 | 08:00 | 2025-10-30 | 20:00 | 12 | pending some painting | 2025-11-02T17:41:00 | 2025-11-02T17:41:00
17 | 5 | Ricardo Morales | CityHall | 17 King St.S. | 2025-10-29 | 08:00 | 2025-10-29 | 20:00 | 12 | pending some panels and lights | 2025-11-02T20:07:01 | 2025-11-02T20:07:01
7 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-29 | 08:00 | 2025-10-29 | 20:00 | 12 | pending some painting | 2025-11-02T17:40:48 | 2025-11-02T17:40:48
12 | 4 | Vincent Vincent | Tycos | 17 Tycos S. | 2025-10-29 | 08:00 | 2025-10-29 | 18:00 | 10 | pending some panels and lights | 2025-11-02T20:03:03 | 2025-11-02T20:03:03
11 | 4 | Vincent Vincent | Tycos | 17 Tycos S. | 2025-10-28 | 08:00 | 2025-10-29 | 18:00 | 34 | pending some panels and lights | 2025-11-02T20:02:42 | 2025-11-02T20:02:42
16 | 5 | Ricardo Morales | CityHall | 17 King St.S. | 2025-10-28 | 08:00 | 2025-10-28 | 22:00 | 14 | pending some panels and lights | 2025-11-02T20:06:39 | 2025-11-02T20:06:39
6 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-28 | 08:00 | 2025-10-28 | 20:00 | 12 | pending some painting | 2025-11-02T17:39:03 | 2025-11-02T17:39:03
15 | 5 | Ricardo Morales | CityHall | 17 King St.S. | 2025-10-27 | 08:00 | 2025-10-27 | 21:00 | 13 | pending some panels and lights | 2025-11-02T20:06:22 | 2025-11-02T20:06:22
10 | 4 | Vincent Vincent | Tycos | 17 Tycos S. | 2025-10-27 | 08:00 | 2025-10-27 | 20:00 | 12 | pending some panels and lights | 2025-11-02T20:02:18 | 2025-11-02T20:02:18
5 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-27 | 08:00 | 2025-10-27 | 20:00 | 12 | pending some painting | 2025-11-02T17:38:51 | 2025-11-02T17:38:51
4 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-26 | 08:00 | 2025-10-26 | 20:00 | 12 | pending some painting | 2025-11-02T17:38:33 | 2025-11-02T17:38:33
3 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-25 | 08:00 | 2025-10-25 | 20:00 | 12 | pending some painting | 2025-11-02T17:38:20 | 2025-11-02T17:38:20
2 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-24 | 08:00 | 2025-10-24 | 19:00 | 11 | pending some drywall | 2025-11-02T17:37:29 | 2025-11-02T17:37:29
1 | 3 | Edgar Mendoza | Tycos | 17 Tycos S. | 2025-10-23 | 08:00 | 2025-10-23 | 19:00 | 11 | pending some drywall | 2025-11-02T17:37:07 | 2025-11-02T17:37:07